## README
NGO Programme M&E Dashboard – Monitoring & Evaluation Portfolio Project
BZME Insights ¦ Sector: NGO / Development ¦ Tool: Excel (formula-driven)
BUSINESS PROBLEM
A donor-funded water, sanitation and hygiene programme works in six counties. The programme manager must report progress against annual targets, show which counties and indicators are lagging, and show whether spending matches delivery. Today this is assembled by hand each quarter.
BUSINESS QUESTIONS
1. How much of each annual target has been delivered, compared with the share of the year that has passed?
2. Which indicators and counties are On track, on Watch or Off track?
3. Is spending ahead of or behind delivery in any county?
4. How far have outcome indicators (household survey) moved from baseline toward target?
5. What is the cost per person reached with safe water?
HOW THE WORKBOOK IS BUILT
Monthly_Results: 432 county-month-indicator records (Jan to Sep 2026).
County_Targets: annual targets by county and indicator (48 rows). Finance: budget and spend by county and quarter. Survey_Data: baseline, midline and target for 3 outcomes by county.
Assumptions: as-of date, year dates, status thresholds and the spend-versus-delivery gap. Blue = input.
Indicators and County_Progress: formula sheets that compute progress, status and budget absorption.
Dashboard: KPIs, key findings, indicator table, county heatmap, outcome table, trend and budget views.
KEY DEFINITIONS
Target to date = annual target x share of year elapsed (straight-line phasing). % of target to date = actual to date / target to date.
Status: On track at or above the first threshold, Watch between the two thresholds, Off track below the second (editable on Assumptions).
Outcome progress = (midline - baseline) / (target - baseline). Budget absorbed = spent to date / annual budget.
Cost per person with safe water = all programme spend to date / people with safe water access. It is a rough programme-level ratio, because the spend also funds hygiene, training and other outputs.
IMPORTANT NOTES
All data is synthetic and generated for demonstration; no real organisation, donor or beneficiary data is used.
Straight-line phasing ignores seasonality; a real programme would load its own quarterly work plan.
Findings update live when assumptions change.
RECOMMENDATIONS (FRAMEWORK)
Focus support visits on Off-track counties and indicators before the next donor report.
Review work plans where spending runs ahead of delivery, and consider reallocating funds from counties that cannot absorb them.
Add quarterly phasing and disaggregation (gender, age, ward) when real data is available.

## Dashboard
NGO Programme M&E Dashboard
Fictional water, sanitation and hygiene (WASH) programme, Western Kenya ¦ Synthetic data ¦ Progress as of 30 Sep 2026 ¦ Prepared by BZME Insights
PEOPLE WITH SAFE WATER ACCESS |  | AVG PROGRESS VS TARGET TO DATE |  | INDICATORS ON TRACK |  | BUDGET ABSORBED (% OF ANNUAL) |  | COST PER PERSON WITH SAFE WATER (KES) |  | OUTCOME PROGRESS TO TARGET
40401 |  | 82.99% |  | 5 of 8 |  | 65.33% |  | 2199.0792 |  | 47.39%
Key findings (update automatically)
1. 75% of the year has passed and the programme has delivered on average 83% of its target to date; 5 of 8 indicators are On track.
2. Strongest indicator: Water quality tests completed (99%). Weakest: School WASH facilities installed (39%).
3. Lowest-performing county: Bungoma (57% of target to date); highest: Kisumu (100%).
4. 1 county is spending ahead of delivery: Bungoma. Review its work plan and cash release.
5. KES 88.8M spent to date (65% of annual budget) at about KES 2,199 per person with new safe water access.
6. Largest remaining gap: People with access to safe water needs 19,599 more by year end to hit the annual target.
7. Outcome survey: Households treating drinking water has the least progress toward target (46% of the baseline-to-target gap closed).
1. Indicator progress: actual vs target to date
Indicator | Annual target | Target to date | Actual to date | % of target to date | Status | Remaining to annual target
People with access to safe water | 60000 | 44876.7123 | 40401 | 90.03% | On track | 19599
Water points built or rehabilitated | 120 | 89.7534 | 63 | 70.19% | Watch | 57
Households reached with hygiene education | 18000 | 13463.0137 | 12714 | 94.44% | On track | 5286
Community health volunteers trained | 360 | 269.2603 | 252 | 93.59% | On track | 108
School WASH facilities installed | 48 | 35.9014 | 14 | 39% | Off track | 34
Water committees formed and trained | 90 | 67.3151 | 66 | 98.05% | On track | 24
Households with new handwashing station | 9000 | 6731.5068 | 5371 | 79.79% | Watch | 3629
Water quality tests completed | 1500 | 1121.9178 | 1109 | 98.85% | On track | 391
Average across indicators |  |  |  | 82.99%
2. County heatmap: % of target to date, by indicator
County | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | Average | Budget absorbed | Spend vs delivery
Kisumu | 104.1% | 50.14% | 110.5% | 126.3% | 80.22% | 118.8% | 89.95% | 120.3% | 100% | 69.12% | Aligned
Siaya | 93.26% | 104% | 100.6% | 108.9% | 38.2% | 143.2% | 85.17% | 108.1% | 97.7% | 66.31% | Aligned
Homa Bay | 71.69% | 60.77% | 79.77% | 69.94% | 14.86% | 108.6% | 67.18% | 70.81% | 67.96% | 45.66% | Aligned
Migori | 92.89% | 89.13% | 89.73% | 71.8% | 57.3% | 66.85% | 81.61% | 98.05% | 80.92% | 67.9% | Aligned
Kakamega | 107.3% | 80.22% | 112.6% | 131.5% | 16.71% | 62.39% | 93.24% | 115.3% | 89.91% | 72.06% | Aligned
Bungoma | 67.53% | 44.57% | 68.68% | 42.09% | 19.1% | 82.28% | 58.93% | 76.65% | 57.48% | 72.19% | Spend > delivery
All counties | 90.03% | 70.19% | 94.44% | 93.59% | 39% | 98.05% | 79.79% | 98.85% | 82.99% | 65.33%
Indicator codes: O1 = People with access to safe water; O2 = Water points built or rehabilitated; O3 = Households reached with hygiene education; O4 = Community health volunteers trained; O5 = School WASH facilities installed; O6 = Water committees formed and trained; O7 = Households with new handwashing station; O8 = Water quality tests completed
3. Outcome indicators (household survey, baseline vs midline)
Outcome | O1: Baseline; O2: Midline; O3: Target; O4: Progress to target
Households treating drinking water | O1: 28.53%; O2: 43.08%; O3: 60%; O4: 46.24%
Households with handwashing facility and soap | O1: 21.68%; O2: 38.18%; O3: 55%; O4: 49.52%
Water points functional after 90 days | O1: 60.72%; O2: 71.98%; O3: 85%; O4: 46.4%
Average | O4: 47.39%
4. Cumulative people with safe water access: actual vs plan
Month | O1: Monthly actual; O2: Cumulative actual; O3: Cumulative plan
2026-01-01 | O1: 2472; O2: 2472; O3: 5000
2026-02-01 | O1: 3410; O2: 5882; O3: 10000
2026-03-01 | O1: 4101; O2: 9983; O3: 15000
2026-04-01 | O1: 4631; O2: 14614; O3: 20000
2026-05-01 | O1: 4832; O2: 19446; O3: 25000
2026-06-01 | O1: 5180; O2: 24626; O3: 30000
2026-07-01 | O1: 5006; O2: 29632; O3: 35000
2026-08-01 | O1: 5363; O2: 34995; O3: 40000
2026-09-01 | O1: 5406; O2: 40401; O3: 45000
5. Budget absorbed vs delivery, by county
County | Time elapsed | Annual budget (KES) | Spent to date (KES) | Budget absorbed | Avg delivery vs target
Kisumu | 74.79% | 28000000 | 19353000 | 69.12% | 100%
Siaya | 74.79% | 20000000 | 13263000 | 66.31% | 97.7%
Homa Bay | 74.79% | 24000000 | 10959000 | 45.66% | 67.96%
Migori | 74.79% | 21000000 | 14259000 | 67.9% | 80.92%
Kakamega | 74.79% | 23000000 | 16573000 | 72.06% | 89.91%
Bungoma | 74.79% | 20000000 | 14438000 | 72.19% | 57.48%
All counties | 74.79% | 136000000 | 88845000 | 65.33% | 82.99%
Reading the table: a county that has absorbed much more budget than it has delivered against target needs a work-plan and cash review before more funds are released.

## Assumptions
Assumptions & Parameters
Blue cells are editable inputs. Everything else recalculates from them.
Assumption | Value | Comment
As-of date | 2026-09-30 | Last day of reported data.
Programme year start | 2026-01-01 | First day of the programme year.
Programme year end | 2026-12-31 | Last day of the programme year.
Share of year elapsed | 74.79% | Calculated. Target-to-date = annual target x this share (straight-line phasing).
On track: at or above | 90% | Share of target-to-date delivered at or above which an indicator is On track.
Watch: at or above | 70% | Between this and the On-track line is Watch; below is Off track.
Spend-vs-delivery gap flag | 15% | Flags a county when budget absorbed and delivery differ by more than this many points.

## Indicators
ID | Indicator | Unit | Annual target | Target to date | Actual to date | % of target to date | % of annual target | Status | Gap to date
O1 | People with access to safe water | people | 60000 | 44876.7123 | 40401 | 90.03% | 67.33% | On track | -4475.7123
O2 | Water points built or rehabilitated | water points | 120 | 89.7534 | 63 | 70.19% | 52.5% | Watch | -26.7534
O3 | Households reached with hygiene education | households | 18000 | 13463.0137 | 12714 | 94.44% | 70.63% | On track | -749.0137
O4 | Community health volunteers trained | volunteers | 360 | 269.2603 | 252 | 93.59% | 70% | On track | -17.2603
O5 | School WASH facilities installed | facilities | 48 | 35.9014 | 14 | 39% | 29.17% | Off track | -21.9014
O6 | Water committees formed and trained | committees | 90 | 67.3151 | 66 | 98.05% | 73.33% | On track | -1.3151
O7 | Households with new handwashing station | households | 9000 | 6731.5068 | 5371 | 79.79% | 59.68% | Watch | -1360.5068
O8 | Water quality tests completed | tests | 1500 | 1121.9178 | 1109 | 98.85% | 73.93% | On track | -12.9178

## County_Progress
County | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | Avg % of target to date | Status | Annual budget (KES) | Spent to date (KES) | Budget absorbed | Absorbed minus delivery | Spend vs delivery
Kisumu | 104.1% | 50.14% | 110.5% | 126.3% | 80.22% | 118.8% | 89.95% | 120.3% | 100% | On track | 28000000 | 19353000 | 69.12% | -7.633% | Aligned
Siaya | 93.26% | 104% | 100.6% | 108.9% | 38.2% | 143.2% | 85.17% | 108.1% | 97.7% | On track | 20000000 | 13263000 | 66.31% | -9.035% | Aligned
Homa Bay | 71.69% | 60.77% | 79.77% | 69.94% | 14.86% | 108.6% | 67.18% | 70.81% | 67.96% | Off track | 24000000 | 10959000 | 45.66% | -6.905% | Aligned
Migori | 92.89% | 89.13% | 89.73% | 71.8% | 57.3% | 66.85% | 81.61% | 98.05% | 80.92% | Watch | 21000000 | 14259000 | 67.9% | 9.863% | Aligned
Kakamega | 107.3% | 80.22% | 112.6% | 131.5% | 16.71% | 62.39% | 93.24% | 115.3% | 89.91% | Watch | 23000000 | 16573000 | 72.06% | 6.43% | Aligned
Bungoma | 67.53% | 44.57% | 68.68% | 42.09% | 19.1% | 82.28% | 58.93% | 76.65% | 57.48% | Off track | 20000000 | 14438000 | 72.19% | 39.04% | Spend > delivery

## Survey_Data
County | OutcomeID | Baseline | Midline | Target
Kisumu | OC1 | 28.1% | 45.1% | 60%
Kisumu | OC2 | 24.3% | 40.8% | 55%
Kisumu | OC3 | 61% | 72.4% | 85%
Siaya | OC1 | 28% | 43.1% | 60%
Siaya | OC2 | 19.7% | 36.7% | 55%
Siaya | OC3 | 63% | 74.5% | 85%
Homa Bay | OC1 | 31.4% | 39.8% | 60%
Homa Bay | OC2 | 22.1% | 37.5% | 55%
Homa Bay | OC3 | 58.9% | 67% | 85%
Migori | OC1 | 26.5% | 43.1% | 60%
Migori | OC2 | 22.3% | 40.2% | 55%
Migori | OC3 | 56.7% | 69.3% | 85%
Kakamega | OC1 | 28.4% | 46.6% | 60%
Kakamega | OC2 | 19.4% | 41.7% | 55%
Kakamega | OC3 | 61.4% | 77.4% | 85%
Bungoma | OC1 | 28.8% | 40.8% | 60%
Bungoma | OC2 | 22.3% | 32.2% | 55%
Bungoma | OC3 | 63.3% | 71.3% | 85%

## Finance
County | Quarter | Budget (KES) | Spent (KES)
Kisumu | Q1 | 7000000 | 6763000
Kisumu | Q2 | 7000000 | 6331000
Kisumu | Q3 | 7000000 | 6259000
Kisumu | Q4 | 7000000 | 0
Siaya | Q1 | 5000000 | 4373000
Siaya | Q2 | 5000000 | 4322000
Siaya | Q3 | 5000000 | 4568000
Siaya | Q4 | 5000000 | 0
Homa Bay | Q1 | 6000000 | 3544000
Homa Bay | Q2 | 6000000 | 3548000
Homa Bay | Q3 | 6000000 | 3867000
Homa Bay | Q4 | 6000000 | 0
Migori | Q1 | 5250000 | 4961000
Migori | Q2 | 5250000 | 4615000
Migori | Q3 | 5250000 | 4683000
Migori | Q4 | 5250000 | 0
Kakamega | Q1 | 5750000 | 5511000
Kakamega | Q2 | 5750000 | 5611000
Kakamega | Q3 | 5750000 | 5451000
Kakamega | Q4 | 5750000 | 0
Bungoma | Q1 | 5000000 | 5110000
Bungoma | Q2 | 5000000 | 4708000
Bungoma | Q3 | 5000000 | 4620000
Bungoma | Q4 | 5000000 | 0

## County_Targets
IndicatorID | County | Annual target
O1 | Kisumu | 12000
O1 | Siaya | 9000
O1 | Homa Bay | 10800
O1 | Migori | 9000
O1 | Kakamega | 10200
O1 | Bungoma | 9000
O2 | Kisumu | 24
O2 | Siaya | 18
O2 | Homa Bay | 22
O2 | Migori | 18
O2 | Kakamega | 20
O2 | Bungoma | 18
O3 | Kisumu | 3600
O3 | Siaya | 2700
O3 | Homa Bay | 3240
O3 | Migori | 2700
O3 | Kakamega | 3060
O3 | Bungoma | 2700
O4 | Kisumu | 72
O4 | Siaya | 54
O4 | Homa Bay | 65
O4 | Migori | 54
O4 | Kakamega | 61
O4 | Bungoma | 54
O5 | Kisumu | 10
O5 | Siaya | 7
O5 | Homa Bay | 9
O5 | Migori | 7
O5 | Kakamega | 8
O5 | Bungoma | 7
O6 | Kisumu | 18
O6 | Siaya | 14
O6 | Homa Bay | 16
O6 | Migori | 14
O6 | Kakamega | 15
O6 | Bungoma | 13
O7 | Kisumu | 1800
O7 | Siaya | 1350
O7 | Homa Bay | 1620
O7 | Migori | 1350
O7 | Kakamega | 1530
O7 | Bungoma | 1350
O8 | Kisumu | 300
O8 | Siaya | 225
O8 | Homa Bay | 270
O8 | Migori | 225
O8 | Kakamega | 255
O8 | Bungoma | 225

## Monthly_Results
Month | County | IndicatorID | Actual
2026-01-01 | Kisumu | O1 | 589
2026-02-01 | Kisumu | O1 | 824
2026-03-01 | Kisumu | O1 | 948
2026-04-01 | Kisumu | O1 | 1050
2026-05-01 | Kisumu | O1 | 1094
2026-06-01 | Kisumu | O1 | 1189
2026-07-01 | Kisumu | O1 | 1148
2026-08-01 | Kisumu | O1 | 1207
2026-09-01 | Kisumu | O1 | 1298
2026-01-01 | Kisumu | O2 | 1
2026-02-01 | Kisumu | O2 | 2
2026-03-01 | Kisumu | O2 | 0
2026-04-01 | Kisumu | O2 | 1
2026-05-01 | Kisumu | O2 | 1
2026-06-01 | Kisumu | O2 | 1
2026-07-01 | Kisumu | O2 | 1
2026-08-01 | Kisumu | O2 | 0
2026-09-01 | Kisumu | O2 | 2
2026-01-01 | Kisumu | O3 | 174
2026-02-01 | Kisumu | O3 | 276
2026-03-01 | Kisumu | O3 | 302
2026-04-01 | Kisumu | O3 | 306
2026-05-01 | Kisumu | O3 | 335
2026-06-01 | Kisumu | O3 | 394
2026-07-01 | Kisumu | O3 | 398
2026-08-01 | Kisumu | O3 | 411
2026-09-01 | Kisumu | O3 | 378
2026-01-01 | Kisumu | O4 | 6
2026-02-01 | Kisumu | O4 | 7
2026-03-01 | Kisumu | O4 | 5
2026-04-01 | Kisumu | O4 | 6
2026-05-01 | Kisumu | O4 | 8
2026-06-01 | Kisumu | O4 | 11
2026-07-01 | Kisumu | O4 | 3
2026-08-01 | Kisumu | O4 | 10
2026-09-01 | Kisumu | O4 | 12
2026-01-01 | Kisumu | O5 | 1
2026-02-01 | Kisumu | O5 | 0
2026-03-01 | Kisumu | O5 | 0
2026-04-01 | Kisumu | O5 | 0
2026-05-01 | Kisumu | O5 | 3
2026-06-01 | Kisumu | O5 | 0
2026-07-01 | Kisumu | O5 | 2
2026-08-01 | Kisumu | O5 | 0
2026-09-01 | Kisumu | O5 | 0
2026-01-01 | Kisumu | O6 | 2
2026-02-01 | Kisumu | O6 | 1
2026-03-01 | Kisumu | O6 | 0
2026-04-01 | Kisumu | O6 | 4
2026-05-01 | Kisumu | O6 | 0
2026-06-01 | Kisumu | O6 | 2
2026-07-01 | Kisumu | O6 | 3
2026-08-01 | Kisumu | O6 | 2
2026-09-01 | Kisumu | O6 | 2
2026-01-01 | Kisumu | O7 | 83
2026-02-01 | Kisumu | O7 | 110
2026-03-01 | Kisumu | O7 | 119
2026-04-01 | Kisumu | O7 | 129
2026-05-01 | Kisumu | O7 | 142
2026-06-01 | Kisumu | O7 | 146
2026-07-01 | Kisumu | O7 | 153
2026-08-01 | Kisumu | O7 | 174
2026-09-01 | Kisumu | O7 | 155
2026-01-01 | Kisumu | O8 | 16
2026-02-01 | Kisumu | O8 | 23
2026-03-01 | Kisumu | O8 | 25
2026-04-01 | Kisumu | O8 | 25
2026-05-01 | Kisumu | O8 | 40
2026-06-01 | Kisumu | O8 | 33
2026-07-01 | Kisumu | O8 | 35
2026-08-01 | Kisumu | O8 | 31
2026-09-01 | Kisumu | O8 | 42
2026-01-01 | Siaya | O1 | 363
2026-02-01 | Siaya | O1 | 528
2026-03-01 | Siaya | O1 | 647
2026-04-01 | Siaya | O1 | 683
2026-05-01 | Siaya | O1 | 764
2026-06-01 | Siaya | O1 | 797
2026-07-01 | Siaya | O1 | 779
2026-08-01 | Siaya | O1 | 862
2026-09-01 | Siaya | O1 | 855
2026-01-01 | Siaya | O2 | 0
2026-02-01 | Siaya | O2 | 0
2026-03-01 | Siaya | O2 | 0
2026-04-01 | Siaya | O2 | 3
2026-05-01 | Siaya | O2 | 3
2026-06-01 | Siaya | O2 | 1
2026-07-01 | Siaya | O2 | 0
2026-08-01 | Siaya | O2 | 4
2026-09-01 | Siaya | O2 | 3
2026-01-01 | Siaya | O3 | 121
2026-02-01 | Siaya | O3 | 173
2026-03-01 | Siaya | O3 | 199
2026-04-01 | Siaya | O3 | 229
2026-05-01 | Siaya | O3 | 245
2026-06-01 | Siaya | O3 | 265
2026-07-01 | Siaya | O3 | 238
2026-08-01 | Siaya | O3 | 291
2026-09-01 | Siaya | O3 | 271
2026-01-01 | Siaya | O4 | 2
2026-02-01 | Siaya | O4 | 8
2026-03-01 | Siaya | O4 | 8
2026-04-01 | Siaya | O4 | 4
2026-05-01 | Siaya | O4 | 4
2026-06-01 | Siaya | O4 | 7
2026-07-01 | Siaya | O4 | 4
2026-08-01 | Siaya | O4 | 5
2026-09-01 | Siaya | O4 | 2
2026-01-01 | Siaya | O5 | 1
2026-02-01 | Siaya | O5 | 0
2026-03-01 | Siaya | O5 | 0
2026-04-01 | Siaya | O5 | 0
2026-05-01 | Siaya | O5 | 1
2026-06-01 | Siaya | O5 | 0
2026-07-01 | Siaya | O5 | 0
2026-08-01 | Siaya | O5 | 0
2026-09-01 | Siaya | O5 | 0
2026-01-01 | Siaya | O6 | 2
2026-02-01 | Siaya | O6 | 0
2026-03-01 | Siaya | O6 | 1
2026-04-01 | Siaya | O6 | 0
2026-05-01 | Siaya | O6 | 1
2026-06-01 | Siaya | O6 | 3
2026-07-01 | Siaya | O6 | 2
2026-08-01 | Siaya | O6 | 5
2026-09-01 | Siaya | O6 | 1
2026-01-01 | Siaya | O7 | 76
2026-02-01 | Siaya | O7 | 77
2026-03-01 | Siaya | O7 | 101
2026-04-01 | Siaya | O7 | 90
2026-05-01 | Siaya | O7 | 104
2026-06-01 | Siaya | O7 | 95
2026-07-01 | Siaya | O7 | 113
2026-08-01 | Siaya | O7 | 94
2026-09-01 | Siaya | O7 | 110
2026-01-01 | Siaya | O8 | 11
2026-02-01 | Siaya | O8 | 17
2026-03-01 | Siaya | O8 | 16
2026-04-01 | Siaya | O8 | 24
2026-05-01 | Siaya | O8 | 23
2026-06-01 | Siaya | O8 | 24
2026-07-01 | Siaya | O8 | 18
2026-08-01 | Siaya | O8 | 22
2026-09-01 | Siaya | O8 | 27
2026-01-01 | Homa Bay | O1 | 358
2026-02-01 | Homa Bay | O1 | 457
2026-03-01 | Homa Bay | O1 | 575
2026-04-01 | Homa Bay | O1 | 706
2026-05-01 | Homa Bay | O1 | 678
2026-06-01 | Homa Bay | O1 | 758
2026-07-01 | Homa Bay | O1 | 740
2026-08-01 | Homa Bay | O1 | 742
2026-09-01 | Homa Bay | O1 | 777
2026-01-01 | Homa Bay | O2 | 1
2026-02-01 | Homa Bay | O2 | 0
2026-03-01 | Homa Bay | O2 | 1
2026-04-01 | Homa Bay | O2 | 1
2026-05-01 | Homa Bay | O2 | 2
2026-06-01 | Homa Bay | O2 | 1
2026-07-01 | Homa Bay | O2 | 1
2026-08-01 | Homa Bay | O2 | 1
2026-09-01 | Homa Bay | O2 | 2
2026-01-01 | Homa Bay | O3 | 144
2026-02-01 | Homa Bay | O3 | 165
2026-03-01 | Homa Bay | O3 | 189
2026-04-01 | Homa Bay | O3 | 218
2026-05-01 | Homa Bay | O3 | 231
2026-06-01 | Homa Bay | O3 | 244
2026-07-01 | Homa Bay | O3 | 242
2026-08-01 | Homa Bay | O3 | 258
2026-09-01 | Homa Bay | O3 | 242
2026-01-01 | Homa Bay | O4 | 0
2026-02-01 | Homa Bay | O4 | 4
2026-03-01 | Homa Bay | O4 | 5
2026-04-01 | Homa Bay | O4 | 4
2026-05-01 | Homa Bay | O4 | 1
2026-06-01 | Homa Bay | O4 | 5
2026-07-01 | Homa Bay | O4 | 6
2026-08-01 | Homa Bay | O4 | 5
2026-09-01 | Homa Bay | O4 | 4
2026-01-01 | Homa Bay | O5 | 0
2026-02-01 | Homa Bay | O5 | 1
2026-03-01 | Homa Bay | O5 | 0
2026-04-01 | Homa Bay | O5 | 0
2026-05-01 | Homa Bay | O5 | 0
2026-06-01 | Homa Bay | O5 | 0
2026-07-01 | Homa Bay | O5 | 0
2026-08-01 | Homa Bay | O5 | 0
2026-09-01 | Homa Bay | O5 | 0
2026-01-01 | Homa Bay | O6 | 0
2026-02-01 | Homa Bay | O6 | 2
2026-03-01 | Homa Bay | O6 | 1
2026-04-01 | Homa Bay | O6 | 0
2026-05-01 | Homa Bay | O6 | 2
2026-06-01 | Homa Bay | O6 | 2
2026-07-01 | Homa Bay | O6 | 2
2026-08-01 | Homa Bay | O6 | 4
2026-09-01 | Homa Bay | O6 | 0
2026-01-01 | Homa Bay | O7 | 53
2026-02-01 | Homa Bay | O7 | 79
2026-03-01 | Homa Bay | O7 | 88
2026-04-01 | Homa Bay | O7 | 102
2026-05-01 | Homa Bay | O7 | 95
2026-06-01 | Homa Bay | O7 | 101
2026-07-01 | Homa Bay | O7 | 95
2026-08-01 | Homa Bay | O7 | 100
2026-09-01 | Homa Bay | O7 | 101
2026-01-01 | Homa Bay | O8 | 11
2026-02-01 | Homa Bay | O8 | 13
2026-03-01 | Homa Bay | O8 | 14
2026-04-01 | Homa Bay | O8 | 16
2026-05-01 | Homa Bay | O8 | 17
2026-06-01 | Homa Bay | O8 | 20
2026-07-01 | Homa Bay | O8 | 19
2026-08-01 | Homa Bay | O8 | 13
2026-09-01 | Homa Bay | O8 | 20
2026-01-01 | Migori | O1 | 397
2026-02-01 | Migori | O1 | 510
2026-03-01 | Migori | O1 | 677
2026-04-01 | Migori | O1 | 720
2026-05-01 | Migori | O1 | 747
2026-06-01 | Migori | O1 | 782
2026-07-01 | Migori | O1 | 777
2026-08-01 | Migori | O1 | 822
2026-09-01 | Migori | O1 | 821
2026-01-01 | Migori | O2 | 0
2026-02-01 | Migori | O2 | 0
2026-03-01 | Migori | O2 | 0
2026-04-01 | Migori | O2 | 0
2026-05-01 | Migori | O2 | 2
2026-06-01 | Migori | O2 | 4
2026-07-01 | Migori | O2 | 3
2026-08-01 | Migori | O2 | 2
2026-09-01 | Migori | O2 | 1
2026-01-01 | Migori | O3 | 96
2026-02-01 | Migori | O3 | 175
2026-03-01 | Migori | O3 | 181
2026-04-01 | Migori | O3 | 203
2026-05-01 | Migori | O3 | 223
2026-06-01 | Migori | O3 | 233
2026-07-01 | Migori | O3 | 224
2026-08-01 | Migori | O3 | 229
2026-09-01 | Migori | O3 | 248
2026-01-01 | Migori | O4 | 2
2026-02-01 | Migori | O4 | 2
2026-03-01 | Migori | O4 | 4
2026-04-01 | Migori | O4 | 5
2026-05-01 | Migori | O4 | 2
2026-06-01 | Migori | O4 | 4
2026-07-01 | Migori | O4 | 3
2026-08-01 | Migori | O4 | 2
2026-09-01 | Migori | O4 | 5
2026-01-01 | Migori | O5 | 0
2026-02-01 | Migori | O5 | 0
2026-03-01 | Migori | O5 | 1
2026-04-01 | Migori | O5 | 1
2026-05-01 | Migori | O5 | 0
2026-06-01 | Migori | O5 | 0
2026-07-01 | Migori | O5 | 0
2026-08-01 | Migori | O5 | 0
2026-09-01 | Migori | O5 | 1
2026-01-01 | Migori | O6 | 0
2026-02-01 | Migori | O6 | 1
2026-03-01 | Migori | O6 | 0
2026-04-01 | Migori | O6 | 0
2026-05-01 | Migori | O6 | 1
2026-06-01 | Migori | O6 | 1
2026-07-01 | Migori | O6 | 0
2026-08-01 | Migori | O6 | 0
2026-09-01 | Migori | O6 | 4
2026-01-01 | Migori | O7 | 57
2026-02-01 | Migori | O7 | 69
2026-03-01 | Migori | O7 | 87
2026-04-01 | Migori | O7 | 94
2026-05-01 | Migori | O7 | 120
2026-06-01 | Migori | O7 | 101
2026-07-01 | Migori | O7 | 99
2026-08-01 | Migori | O7 | 109
2026-09-01 | Migori | O7 | 88
2026-01-01 | Migori | O8 | 8
2026-02-01 | Migori | O8 | 17
2026-03-01 | Migori | O8 | 17
2026-04-01 | Migori | O8 | 20
2026-05-01 | Migori | O8 | 18
2026-06-01 | Migori | O8 | 20
2026-07-01 | Migori | O8 | 17
2026-08-01 | Migori | O8 | 21
2026-09-01 | Migori | O8 | 27
2026-01-01 | Kakamega | O1 | 484
2026-02-01 | Kakamega | O1 | 695
2026-03-01 | Kakamega | O1 | 821
2026-04-01 | Kakamega | O1 | 964
2026-05-01 | Kakamega | O1 | 1038
2026-06-01 | Kakamega | O1 | 1094
2026-07-01 | Kakamega | O1 | 946
2026-08-01 | Kakamega | O1 | 1093
2026-09-01 | Kakamega | O1 | 1051
2026-01-01 | Kakamega | O2 | 0
2026-02-01 | Kakamega | O2 | 2
2026-03-01 | Kakamega | O2 | 2
2026-04-01 | Kakamega | O2 | 3
2026-05-01 | Kakamega | O2 | 1
2026-06-01 | Kakamega | O2 | 1
2026-07-01 | Kakamega | O2 | 0
2026-08-01 | Kakamega | O2 | 2
2026-09-01 | Kakamega | O2 | 1
2026-01-01 | Kakamega | O3 | 180
2026-02-01 | Kakamega | O3 | 211
2026-03-01 | Kakamega | O3 | 255
2026-04-01 | Kakamega | O3 | 286
2026-05-01 | Kakamega | O3 | 330
2026-06-01 | Kakamega | O3 | 336
2026-07-01 | Kakamega | O3 | 318
2026-08-01 | Kakamega | O3 | 320
2026-09-01 | Kakamega | O3 | 340
2026-01-01 | Kakamega | O4 | 2
2026-02-01 | Kakamega | O4 | 10
2026-03-01 | Kakamega | O4 | 5
2026-04-01 | Kakamega | O4 | 7
2026-05-01 | Kakamega | O4 | 7
2026-06-01 | Kakamega | O4 | 7
2026-07-01 | Kakamega | O4 | 5
2026-08-01 | Kakamega | O4 | 7
2026-09-01 | Kakamega | O4 | 10
2026-01-01 | Kakamega | O5 | 0
2026-02-01 | Kakamega | O5 | 0
2026-03-01 | Kakamega | O5 | 0
2026-04-01 | Kakamega | O5 | 0
2026-05-01 | Kakamega | O5 | 0
2026-06-01 | Kakamega | O5 | 0
2026-07-01 | Kakamega | O5 | 0
2026-08-01 | Kakamega | O5 | 1
2026-09-01 | Kakamega | O5 | 0
2026-01-01 | Kakamega | O6 | 0
2026-02-01 | Kakamega | O6 | 1
2026-03-01 | Kakamega | O6 | 2
2026-04-01 | Kakamega | O6 | 0
2026-05-01 | Kakamega | O6 | 2
2026-06-01 | Kakamega | O6 | 0
2026-07-01 | Kakamega | O6 | 0
2026-08-01 | Kakamega | O6 | 2
2026-09-01 | Kakamega | O6 | 0
2026-01-01 | Kakamega | O7 | 82
2026-02-01 | Kakamega | O7 | 100
2026-03-01 | Kakamega | O7 | 97
2026-04-01 | Kakamega | O7 | 110
2026-05-01 | Kakamega | O7 | 115
2026-06-01 | Kakamega | O7 | 131
2026-07-01 | Kakamega | O7 | 123
2026-08-01 | Kakamega | O7 | 165
2026-09-01 | Kakamega | O7 | 144
2026-01-01 | Kakamega | O8 | 11
2026-02-01 | Kakamega | O8 | 13
2026-03-01 | Kakamega | O8 | 24
2026-04-01 | Kakamega | O8 | 32
2026-05-01 | Kakamega | O8 | 23
2026-06-01 | Kakamega | O8 | 30
2026-07-01 | Kakamega | O8 | 29
2026-08-01 | Kakamega | O8 | 30
2026-09-01 | Kakamega | O8 | 28
2026-01-01 | Bungoma | O1 | 281
2026-02-01 | Bungoma | O1 | 396
2026-03-01 | Bungoma | O1 | 433
2026-04-01 | Bungoma | O1 | 508
2026-05-01 | Bungoma | O1 | 511
2026-06-01 | Bungoma | O1 | 560
2026-07-01 | Bungoma | O1 | 616
2026-08-01 | Bungoma | O1 | 637
2026-09-01 | Bungoma | O1 | 604
2026-01-01 | Bungoma | O2 | 1
2026-02-01 | Bungoma | O2 | 0
2026-03-01 | Bungoma | O2 | 1
2026-04-01 | Bungoma | O2 | 0
2026-05-01 | Bungoma | O2 | 0
2026-06-01 | Bungoma | O2 | 0
2026-07-01 | Bungoma | O2 | 1
2026-08-01 | Bungoma | O2 | 1
2026-09-01 | Bungoma | O2 | 2
2026-01-01 | Bungoma | O3 | 81
2026-02-01 | Bungoma | O3 | 115
2026-03-01 | Bungoma | O3 | 126
2026-04-01 | Bungoma | O3 | 177
2026-05-01 | Bungoma | O3 | 166
2026-06-01 | Bungoma | O3 | 171
2026-07-01 | Bungoma | O3 | 179
2026-08-01 | Bungoma | O3 | 180
2026-09-01 | Bungoma | O3 | 192
2026-01-01 | Bungoma | O4 | 0
2026-02-01 | Bungoma | O4 | 2
2026-03-01 | Bungoma | O4 | 0
2026-04-01 | Bungoma | O4 | 3
2026-05-01 | Bungoma | O4 | 3
2026-06-01 | Bungoma | O4 | 2
2026-07-01 | Bungoma | O4 | 2
2026-08-01 | Bungoma | O4 | 1
2026-09-01 | Bungoma | O4 | 4
2026-01-01 | Bungoma | O5 | 0
2026-02-01 | Bungoma | O5 | 1
2026-03-01 | Bungoma | O5 | 0
2026-04-01 | Bungoma | O5 | 0
2026-05-01 | Bungoma | O5 | 0
2026-06-01 | Bungoma | O5 | 0
2026-07-01 | Bungoma | O5 | 0
2026-08-01 | Bungoma | O5 | 0
2026-09-01 | Bungoma | O5 | 0
2026-01-01 | Bungoma | O6 | 0
2026-02-01 | Bungoma | O6 | 1
2026-03-01 | Bungoma | O6 | 1
2026-04-01 | Bungoma | O6 | 0
2026-05-01 | Bungoma | O6 | 1
2026-06-01 | Bungoma | O6 | 1
2026-07-01 | Bungoma | O6 | 1
2026-08-01 | Bungoma | O6 | 2
2026-09-01 | Bungoma | O6 | 1
2026-01-01 | Bungoma | O7 | 42
2026-02-01 | Bungoma | O7 | 49
2026-03-01 | Bungoma | O7 | 71
2026-04-01 | Bungoma | O7 | 54
2026-05-01 | Bungoma | O7 | 76
2026-06-01 | Bungoma | O7 | 65
2026-07-01 | Bungoma | O7 | 76
2026-08-01 | Bungoma | O7 | 88
2026-09-01 | Bungoma | O7 | 74
2026-01-01 | Bungoma | O8 | 10
2026-02-01 | Bungoma | O8 | 9
2026-03-01 | Bungoma | O8 | 21
2026-04-01 | Bungoma | O8 | 16
2026-05-01 | Bungoma | O8 | 19
2026-06-01 | Bungoma | O8 | 17
2026-07-01 | Bungoma | O8 | 15
2026-08-01 | Bungoma | O8 | 9
2026-09-01 | Bungoma | O8 | 13